## Tabelle1
event | group | start | end | color
development of sampling criteria | survey preparation | 2019-03-01 | 2019-05-03
capture of the gross sample | survey preparation | 2019-03-01 | 2019-06-01
collection of address lists | survey preparation | 2019-04-01 | 2019-07-01
development of instruments | survey preparation | 2019-05-01 | 2020-05-01
questionnaire programming using ZOFAR | survey preparation | 2020-03-01 | 2020-08-01
pre-tests | survey preparation | 2020-08-01 | 2020-09-01
completion of the survey preparation | survey preparation | 2020-09-01 | 2020-09-01 | #f44336
field phase | survey conducting | 2020-09-01 | 2020-10-01
data cleaning | survey conducting | 2020-10-01 | 2020-12-01
completion of the conduct of the survey | survey conducting | 2020-12-01 | 2020-12-01 | #f44336
data cleaning, modelling | Paper No.1 | 2020-12-01 | 2021-02-01
data interpretation/reporting | Paper No.1 | 2021-02-01 | 2021-06-01
internale review/proof reading | Paper No.1 | 2021-06-01 | 2022-02-01
Einreichung | Paper No.1 | 2022-02-01 | 2022-02-01 | #f44336
data cleaning, modelling | Paper No.2 | 2021-06-01 | 2021-08-01
data interpretation/reporting | Paper No.2 | 2021-08-01 | 2021-10-01
internal review/proof reading | Paper No.2 | 2021-10-01 | 2022-01-01
submission | Paper No.2 | 2022-01-01 | 2022-01-01 | #f44336
data cleaning, modelling | Paper No.3 | 2021-06-01 | 2021-08-01
data interpretation/reporting | Paper No.3 | 2021-08-01 | 2021-10-01
internal review/proof reading | Paper No.3 | 2021-10-01 | 2022-05-01
data cleaning, modelling | Paper No.4 | 2021-09-01 | 2021-11-01
data interpretation/reporting | Paper No.4 | 2021-11-01 | 2022-03-01
internal review/proof reading | Paper No.4 | 2022-03-01 | 2022-05-01
submission | Paper No.4 | 2022-05-01 | 2022-05-01 | #f44336
writing overall introduction and discussion | Finalisation | 2022-05-01 | 2022-07-01
editing/proofreading | Finalisation | 2022-07-01 | 2022-08-01
final submission | Finalisation | 2022-08-01 | 2022-08-01 | #f44336